## Read Me
NIST CSF 2.0 Risk Register & Gap Analysis — Home Network Assessment
Subject: a real home network, assessed as a personal GRC portfolio project
HOW TO USE THIS WORKBOOK
1. CSF Assessment tab — the 6 NIST CSF 2.0 Functions and their Categories, applied to a home network
environment (basic ISP router, multiple family members, occasional sensitive-data use).
2. Risk Register tab — every gap converted into a scored risk (Likelihood x Impact). Formulas
auto-calculate the score and priority band — don't overwrite them, just add rows.
3. Remediation Roadmap tab — risks grouped into Quick Win / Short-Term / Long-Term buckets.
COLOR KEY
Yellow/orange fill on Priority = High risk. Yellow on Status = Partially Met.
White cells with formulas = do not edit directly; they recalculate from the Risk Register tab.
This project demonstrates the same methodology used in a professional GRC gap analysis
(NIST CSF 2.0 mapping, likelihood/impact scoring, phased remediation), applied to a real,
everyday environment to show practical, not just theoretical, framework fluency.

## CSF Assessment
Function | Category | Current State | Status | Gap / Risk Exposure
Govern | Organizational Context / Risk Strategy | No household security rules exist; no one has defined what's acceptable (e.g., what devices connect, how passwords are handled). | Not Met | Without agreed-upon rules, security depends entirely on individual habits, which vary widely across household members.
Govern | Roles, Responsibilities & Authorities | Fatima is the de facto network administrator by default (most technically knowledgeable), but this is informal. | Partially Met | No backup or shared understanding of who manages the network if she's unavailable during an issue.
Identify | Asset Management | No inventory of devices connected to the network (phones, laptops, TV); no record of what 'normal' looks like. | Not Met | An unfamiliar or unauthorized device could join the network without anyone noticing.
Identify | Risk Assessment | No prior risk assessment of the home network has been performed; this project is the first. | Not Met | No visibility into which household security gaps matter most.
Protect | Identity Management & Access Control | Router admin credentials are still factory default; Fatima uses a password generator and passkeys personally, but other family members reuse passwords across accounts. | Partially Met | Default router credentials are publicly searchable by make/model, giving easy unauthorized access; reused passwords mean one breached account can compromise several.
Protect | Network Segmentation | Single flat network — no separate guest network for visitors or lower-trust devices. | Not Met | A compromised guest or visitor device has the same network access as personal devices handling sensitive data.
Protect | Awareness & Habits | No shared understanding among family members of safe password practices or phishing risks. | Not Met | Household members are the most likely entry point for account compromise via weak/reused credentials.
Protect | Platform & Technology Security | Router firmware updates automatically; no smart-home/IoT devices in use (smaller attack surface). | Met | This is a genuine strength — automatic patching closes off a common vulnerability class, and the lack of IoT devices limits exposure.
Detect | Continuous Monitoring | No one checks the router's connected-devices list; no visibility into unusual network activity. | Not Met | An unfamiliar device or unusual data usage could go unnoticed indefinitely.
Respond | Incident Management | No plan for what to do if something looks wrong (locked-out account, unknown device, suspicious activity). | Not Met | A real incident would be handled reactively and without a clear first step, increasing confusion and response time.
Recover | Recovery Planning | Personal documents and photos are backed up to cloud/external storage. | Met | This is a genuine strength — data loss from a compromised or failed device would not be catastrophic thanks to existing backups.

## Risk Register
Risk ID | Risk Description | CSF Function | Likelihood (1-5) | Impact (1-5) | Risk Score | Priority | Owner | Status
R-01 | Router still has default admin credentials | Protect | 4 | 5 | 20 | High | Fatima | Open
R-02 | No guest network to isolate visitor devices | Protect | 3 | 3 | 9 | Medium | Fatima | Open
R-03 | Inconsistent password hygiene among family members | Protect | 4 | 4 | 16 | High | Household | Open
R-04 | No visibility into connected devices / unusual activity | Detect | 3 | 3 | 9 | Medium | Fatima | Open
R-05 | No incident response plan for household security issues | Respond | 2 | 3 | 6 | Low | Fatima | Open
R-06 | No documented household security rules | Govern | 2 | 2 | 4 | Low | Household | Open
R-07 | No device inventory maintained | Identify | 2 | 2 | 4 | Low | Fatima | Open
Risk Score = Likelihood x Impact. Priority: High >=15, Medium 8-14, Low <=7. Sort by Risk Score (col F) descending to see top priorities.

## Remediation Roadmap
Phase | Risk ID(s) | Action | Est. Effort | Owner
Quick Win (0-30 days) | R-01 | Change router admin username/password from factory default to a unique, strong credential | Low | Fatima
Quick Win (0-30 days) | R-02 | Set up a separate guest network for visitors and lower-trust devices | Low | Fatima
Quick Win (0-30 days) | R-03 | Get family members using unique passwords or a password manager for email/school/other key accounts | Low | Household
Short-Term (30-90 days) | R-04 | Check the router's built-in connected-devices list periodically to spot unfamiliar devices | Low | Fatima
Short-Term (30-90 days) | R-05 | Write a one-page household plan: who to contact and what steps to take if something looks wrong | Medium | Fatima
Long-Term (90+ days) | R-06 | Agree on 3-4 simple household security rules (e.g., no sharing Wi-Fi password with guests, personal devices only for sensitive tasks) | Low | Household
Long-Term (90+ days) | R-07 | Keep a simple running list of what devices are connected to the network | Low | Fatima